## Sheet1
| Project Name | Project Duration | Project Start Date | Project End Date
| Park4Me | 56 | 2018-01-06 | 2018-03-02
Sprint | Task | Start Date | End Date | Duration | Status | Percent Complete | time axis 2018-01-10 to 2018-03-03
Sprint 01 | Project Proposal Development | 2018-01-10 | 2018-01-23 | 14 | Completed |  | 2018-01-10: Completed; 2018-01-11: Completed; 2018-01-12: Completed; 2018-01-14: Completed
| Requirement Gathering | 2018-01-11 | 2018-01-11 | 1 | Completed |  | 2018-01-11: Completed; 2018-01-12: Completed; 2018-01-14: Completed
| Client Discussion | 2018-01-12 | 2018-01-12 | 1 | Completed |  | 2018-01-12: Completed; 2018-01-14: Completed
| Desing Logo | 2018-01-13 | 2018-01-14 | 2 | Completed |  | 2018-01-14: Completed
| Develop Timeline | 2018-01-14 | 2018-01-14 | 1 | Completed |  | 2018-01-14: Completed
| Create Praposal | 2018-01-15 | 2018-01-15 | 1 | Completed
Sprint 02 | Prototype Development | 2018-01-24 | 2018-02-06 | 14 | Completed
| DB Design | 2018-01-25 | 2018-01-26 | 2 | Completed
| Design Web UI | 2018-01-26 | 2018-01-27 | 2 | Completed
| Desing Android App | 2018-01-27 | 2018-01-28 | 2 | Completed
Sprint 03 | QA Testing and Bug Fixing | 2018-02-07 | 2018-02-18 | 12 | Completed
|  | 2018-02-08 | 2018-02-09 | 2 | Completed
Sprint 04 | QA Testing | 2018-02-17 | 2018-03-02 | 14 | Completed
|  |  | 0 | 1 | Completed |  | 2018-01-11: Completed; 2018-01-14: Completed
Sprint 05 | Implementation | 2018-03-02 | 2018-03-02 | 1 | Completed
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Project End Date = [Project Start Date]+[Project Duration]-1
Project Start Date = [Project Duration]+[Project End Date]-1

## Sheet1 (2)
| Project Name | Project Duration |  | Project Start Date |  | Project End Date
| Place4Me | 56 |  | 2018-01-09 |  | 2018-03-06
Sprint | Task | Start Date | End Date | Duration | Status | Percent Complete | time axis 2018-01-10 to 2018-03-03
Sprint 01 | Project Proposal Development | 2018-01-09 | 2018-01-22 | 14 | Completed | 65% | 2018-01-10: Completed; 2018-01-11: Completed; 2018-01-12: Completed; 2018-01-13: Completed; 2018-01-14: Completed; 2018-01-15: Completed; 2018-01-16: Completed; 2018-01-17: Completed; 2018-01-18: Completed; 2018-01-19: Completed; 2018-01-20: Completed; 2018-01-21: Completed; 2018-01-22: Completed
| Requirement Gathering | 2018-01-11 | 2018-01-17 | 7 | Completed |  | 2018-01-11: Completed; 2018-01-12: Completed; 2018-01-13: Completed; 2018-01-14: Completed; 2018-01-15: Completed; 2018-01-16: Completed; 2018-01-17: Completed
| Client Discussion | 2018-01-12 | 2018-01-16 | 5 | Pending |  | 2018-01-12: Pending; 2018-01-13: Pending; 2018-01-14: Pending; 2018-01-15: Pending; 2018-01-16: Pending
| Desing Logo | 2018-01-16 | 2018-01-20 | 5 | Completed |  | 2018-01-16: Completed; 2018-01-17: Completed; 2018-01-18: Completed; 2018-01-19: Completed; 2018-01-20: Completed
| Develop Timeline | 2018-01-15 | 2018-01-19 | 5 | Pending |  | 2018-01-15: Pending; 2018-01-16: Pending; 2018-01-17: Pending; 2018-01-18: Pending; 2018-01-19: Pending
| Create Praposal | 2018-01-17 | 2018-01-22 | 6 | Pending |  | 2018-01-17: Pending; 2018-01-18: Pending; 2018-01-19: Pending; 2018-01-20: Pending; 2018-01-21: Pending; 2018-01-22: Pending
Sprint 02 | Prototype Development | 2018-01-22 | 2018-02-04 | 14 | Pending |  | 2018-01-22: Pending; 2018-01-23: Pending; 2018-01-24: Pending; 2018-01-25: Pending; 2018-01-26: Pending; 2018-01-27: Pending; 2018-01-28: Pending; 2018-01-29: Pending; 2018-01-30: Pending; 2018-01-31: Pending; 2018-02-01: Pending; 2018-02-02: Pending; 2018-02-03: Pending; 2018-02-04: Pending
| DB Design | 2018-01-23 | 2018-01-27 | 5 |  |  | 2018-01-23: 0; 2018-01-24: 0; 2018-01-25: 0; 2018-01-26: 0; 2018-01-27: 0
| Design Web UI | 2018-01-24 | 2018-01-28 | 5 |  |  | 2018-01-24: 0; 2018-01-25: 0; 2018-01-26: 0; 2018-01-27: 0; 2018-01-28: 0
| Desing Android App | 2018-01-25 | 2018-01-29 | 5 |  |  | 2018-01-25: 0; 2018-01-26: 0; 2018-01-27: 0; 2018-01-28: 0; 2018-01-29: 0
| Image Prosessing | 2018-01-26 | 2018-01-30 | 5 |  |  | 2018-01-26: 0; 2018-01-27: 0; 2018-01-28: 0; 2018-01-29: 0; 2018-01-30: 0
Sprint 03 | Development and Bug Fixing | 2018-02-04 | 2018-02-17 | 14 | Pending |  | 2018-02-04: Pending; 2018-02-05: Pending; 2018-02-06: Pending; 2018-02-07: Pending; 2018-02-08: Pending; 2018-02-09: Pending; 2018-02-10: Pending; 2018-02-11: Pending; 2018-02-12: Pending; 2018-02-13: Pending; 2018-02-14: Pending; 2018-02-15: Pending; 2018-02-16: Pending; 2018-02-17: Pending
Smoke Testing
UI Testing
Functionl Testing
Sprint 04 | Acception Testing | 2018-02-17 | 2018-03-02 | 14 | Pending |  | 2018-02-17: Pending; 2018-02-18: Pending; 2018-02-19: Pending; 2018-02-20: Pending; 2018-02-21: Pending; 2018-02-22: Pending; 2018-02-23: Pending; 2018-02-24: Pending; 2018-02-25: Pending; 2018-02-26: Pending; 2018-02-27: Pending; 2018-02-28: Pending; 2018-03-01: Pending; 2018-03-02: Pending
Sprint 05 | Implementation | 2018-03-03 | 2018-03-03 | 1 | Pending |  | 2018-03-03: Pending
Formulas:
Project End Date = [Project Start Date]+[Project Duration]